## Task
# | Task | Priority | Status | Task Assigned | Start Date | End Date | Review/Testing | Comments
1 | Alignment and UI Enhancement | High | Ongoing | Misnad
2 | Photo Aspect Ratio | High | Testing | Misnad
3 | Display Enhancement of Scanned ID | High | Testing | Misnad
4 | Progress bar while background progress | Medium | YetToStart | Ranjith
5 | Message Box alteration: Add Title, Alert/Error/Info | High | OnGoing | Ranjith/Misnad
6 | Camera-Scanner Status: active, inactive | High | YetToStart | Ranjith
7 | Back side ID image processing | Low | YetToStart | Ranjith
8 | Title Combo box Addition: supervisor, Manager, etc. etc. | High | YetToStart | Ranjith
9 | Adding Default data to fields | High | YetToStart | Ranjith
10 | All Fields Validation | High | Testing | Misnad
11 | Save to DB and Confirmation Message alteration | High | Testing | Misnad
12 | Change field name to Approval manager | High | YetToStart
13 | Security Controller combo box addition | High | YetToStart | Ranjith |  |  |  | created the combo box
14 | Segregate panel to display scanned images | High | Closed | Misnad
15 | Buttons for Scan MRZ/ Read from Chip | High | YetToStart | Ranjith/Misnad
16 | Form resize use window state | High | Closed | Misnad
17 | Dynamic Search from list dropdown | Medium | YetToStart | Ranjith
18 | Title Combo box New Addition of data dynamic | Medium | YetToStart | Ranjith

## DDL (hidden)
Developing | High
Testing | Medium
Closed | Low
Open
OnGoing
YetToStart